## Template
<Project Name> Communication Plan
Use this sheet to track who needs updates, what they need to know, and how you will communicate with them throughout the project.
Communication Plan
Stakeholder |  |  | Communication Plan |  |  |  | Updates
Name or Group | Team / Dept. | Role | What They Need to Know | Communication Method | Frequency / Timing | Owner (Who is sending) | Last Date Sent | Notes

## Example
<Project Name> Communication Plan
Use this sheet to track who needs updates, what they need to know, and how you will communicate with them throughout the project.
Communication Plan
Stakeholder |  |  | Communication Plan |  |  |  | Updates
Name or Group | Team / Dept. | Role | What They Need to Know | Communication Method | Frequency / Timing | Owner (Who is sending) | Last Date Sent | Notes
John Smith | President | Executive Sponsor | Major milestones, risks, decisions needing approval | Email / Executive Briefing | Monthly / At Milestones | Project Manager | 4/15/2026 | Keep high-level, focus on outcomes
Sally Jones | VP of Admissions | Project Sponsor | Progress updates, risks, alignment to goals | Meeting | Monthly | Project Manager | 4/10/2026 | Include summary slide
Presidential Advisory Council (PAC) | Cabinet Members | Leadership Stakeholders | High-level project impact and status | Email / Presentation | At Key Milestones | Project Sponsor |  | Keep concise
Project Team | Internal Staff | Project Team | Weekly tasks, priorities, blockers | Teams / Meeting | Weekly | Project Manager | 4/12/2026 | Include action items
OIT | Technical Leads | Technical Team | Technical requirements, timelines, dependencies | Teams / Meeting | Bi-weekly | IT Lead | 4/11/2026 | Track integration points
Faculty & Staff | End Users | Impacted Users | Changes, rollout timing, resources | Email / Webpage | As Needed | UComm / Project Team |  | Link FAQ page
Students (if applicable) | End Users | Impacted Users | Service changes and how to access | Email / Website | At Launch | UComm |  | Keep messaging simple
External Vendor | Vendor Team | Implementation Partner | Deliverables, deadlines, expectations | Email / Meeting | Weekly | Project Manager | 4/13/2026 | Monitor closely
Operations Team | Department Leads | Process Owners | Changes to workflows and responsibilities | Meeting | Bi-weekly | Project Manager |  | Ensure alignment early